## Sheet1
Task ID | Task Description | Task Length | Start Date | End Date | Sean's Effort | Hung's Effort
1 | Design overall basis of game style and design (may be changed or expanded in the future) | 7 | 2019-10-01 | 2019-10-07 | 50% | 50%
2 | Research and Design major objects and functions for game
2.1 | Design objects and functions to run game program | 7 | 2019-10-08 | 2019-10-14 | 75% | 25%
2.2 | Design objects and functions for displaying game | 7 | 2019-10-15 | 2019-10-21 | 75% | 25%
2.3 | Design objects and functions for basic game objects | 7 | 2019-10-22 | 2019-10-28 | 50% | 50%
2.4 | Research and design a proper method for storing game objects and assets | 7 | 2019-10-29 | 2019-11-04 | 25% | 75%
2.5 | Design objects and functions for object collisions and interactions | 7 | 2019-11-05 | 2019-11-11 | 25% | 75%
2.6 | Design objects and functions for handling game music and sound effects | 7 | 2019-11-12 | 2019-11-18 | 75% | 25%
2.7 | Design objects and functions for displaying and handling interactions with various game menus | 7 | 2019-11-19 | 2019-11-25 | 25% | 75%
3 | Develop the main components of the game engine | 14 | 2019-11-26 | 2019-12-09 | 50% | 50%
3.1 | Test and Refine these components | 2 | 2019-12-10 | 2019-12-11 | 50% | 50%
4 | Design basic/sample assets for the game to use | 4 | 2019-12-12 | 2019-12-15 | 25% | 75%
5 | Design player model and animations | 6 | 2019-12-16 | 2019-12-21 | 75% | 25%
6 | Design game world object’s models and animations | 6 | 2019-12-22 | 2019-12-27 | 50% | 50%
7 | Test and refine game objects and assets | 2 | 2019-12-28 | 2019-12-29 | 50% | 50%
8 | Design objects and functions for analyzing game music | 4 | 2019-12-30 | 2020-01-02 | 75% | 25%
9 | Design objects and functions to use this data to output proper actions for game objects | 6 | 2020-01-03 | 2020-01-08 | 75% | 25%
10 | Test and refine game objects and assets based on the actions from the game music | 4 | 2020-01-09 | 2020-01-12 | 50% | 50%
11 | Design additional game objects and functions to meet originally planned game mechanics
11.1 | Additional player items (weapons, armor, …) to increase gameplay/player variety | 4 | 2020-01-13 | 2020-01-16 | 50% | 50%
11.2 | Additional game environments and game world objects | 5 | 2020-01-17 | 2020-01-21 | 50% | 50%
12 | Create product demos | 14 | 2020-01-22 | 2020-02-04 | 50% | 50%
Formulas:
End Date = [Start Date] +[Task Length] - 1
Start Date = [Start Date, row above]+[Task Length, row above]